## Execution Plan
HCL GUVI × FPT UNIVERSITY (FPTU) — VIETNAM
Project-Driven VLSI On-the-Job Training (OJT) — 14-Week Execution Plan
RTL to GDSII · 5 Escalating Projects · 50 Candidates · Vietnam public-holiday calendar applied · Sat & Sun excluded
1. Program Snapshot
Metric | Value
Total Program Hours | 560 hrs
Duration | 14 Weeks · 70 working days
Weekly Cadence | Mon–Fri, 8 hrs/day (excl. Sat/Sun & Vietnam public holidays)
Orientation + Pre-Assessment | 18-Sep-2026 (Friday)
Week 1 Day 1 (program start) | 21-Sep-2026 (Monday)
Week 14 Day 5 / Demo Day | 29-Dec-2026 (Tuesday)
Candidates | 26
Projects delivered | 5 (P1 → P5, escalating complexity, RTL to GDSII)
Vietnam holidays inside this window | 23–24 Nov 2026 — Vietnam Culture Day (bridge day + holiday)
2. Hour Distribution (per your allocation table)
Category | Target Hrs | Planned Hrs | % of Program | What it covers
VILT — Virtual/Live Instructor-Led Training | 125 | 125 | 22% | Trainer-led sessions, max 2-3 hrs/day: 85% Technical (106 hrs — live demos, guided coding) + 15% Communication (19 hrs — soft-skills/interview coaching). See 'VILT Session Plan' tab.
SPL — Self-Paced Learning | 75 | 75 | 13% | Pre-recorded videos, reading material, guideline PDFs — done independently by the candidate
OJT — On-the-Job Training | 110 | 110 | 20% | Daily stand-ups, mentor 1:1s, peer reviews, Communication-Skills sessions, and Company Visits — all folded under OJT as instructed
Project Implementation | 250 | 250 | 45% | Independent hands-on project build, debugging, GitHub/documentation work
TOTAL | 560 | 560 | 100%
Note: Planned hours are built day-by-day from the 70-day schedule (see 'Session Plan' tab) and land exactly on each target (SPL 75 / VILT 125 / OJT 110 / Project-Implementation 250 = 560).
3. Project Roadmap (P1 -> P5)
Project | Title | Weeks | Days | Goal
P1 | Digital Logic Foundation & Scripting | Wk 1-2 | D1-D10 | Build a 4-bit CPU Datapath from gate-level. Python & TCL scripting.
P2 | 8-bit RISC Processor Core (RTL Design) | Wk 3-5 | D11-D25 | Design a synthesizable 8-bit RISC processor with a 5-stage pipeline.
P3 | SystemVerilog + UVM Verification Testbench | Wk 6-8 | D26-D40 | Full UVM environment for a DUT — constrained-random, scoreboard, functional coverage >= 90%.
P4 | Full SoC IP Design (RTL to PD Sign-off) | Wk 9-11 | D41-D55 | SPI/UART/I2C Communication IP through complete RTL -> Synthesis -> STA -> PD -> DRC/LVS sign-off flow.
P5 | Capstone: Full RISC-V Core RTL to GDSII | Wk 12-14 | D56-D70 | End-to-end RTL -> GDSII using OpenLane + OpenROAD on Sky130. Expert panel demo.
4. Weekly Hour Allocation (SPL / VILT / OJT / Project Implementation)
Week | Project | SPL Hrs | VILT Hrs | OJT Hrs | Proj-Impl Hrs | Total Hrs
Week 1 | P1 | 5.9 | 10 | 5 | 19.1 | 40
Week 2 | P1 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 3 | P2 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 4 | P2 | 4.7 | 8 | 12 | 15.3 | 40
Week 5 | P2 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 6 | P3 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 7 | P3 | 4.7 | 8 | 12 | 15.3 | 40
Week 8 | P3 | 5.5 | 9 | 7 | 18.5 | 40
Week 9 | P4 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 10 | P4 | 4.7 | 8 | 12 | 15.3 | 40
Week 11 | P4 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 12 | P5 | 5.7 | 9.5 | 6 | 18.8 | 40
Week 13 | P5 | 4.4 | 7 | 14 | 14.6 | 40
Week 14 | P5 | 5 | 8.5 | 6 | 20.5 | 40
5. Milestone Gates & Assessment
Project | Milestone Day | Pass Criteria | How Assessed | If Not Passing
P1 | D10 (End Wk 2) | Gate-level design compiles and simulates correctly | GitHub repo reviewed by mentor | Re-run tool install; instructor 1:1 session
P2 | D25 (End Wk 5) | Lint-clean Verilog RTL + self-checking testbench | Code review + lint report submitted | Code review session; extra day given
P3 | D40 (End Wk 8) | UVM regression passes; functional coverage >= 90% | Simulation logs + coverage report reviewed | Mentor-guided debug; coverage closure lab
P4 | D55 (End Wk 11) | GDS baseline produced; DRC/LVS 0 violations | Physical verification reports submitted | DRC workshop; peer pair debugging session
P5 | D70 (End Wk 14) | GDSII + STA signoff (WNS>=0) + panel presentation | Live panel + Q&A + GitHub portfolio review | Certificate held; resubmit within 5 days
Certification rubric: Technical Implementation 40% · Verification Coverage 25% · Documentation Quality 20% · Presentation 15%
Grade bands: Distinction >=85% · Merit 75-84% · Pass 65-74% · Certificate withheld <65%. Minimum 75% attendance + all 5 projects submitted + capstone panel presented.
6. Communication-Skills Schedule (~12 hrs, tagged OJT)
Day | Topic | Duration
D8 (Wk2) | Email writing — professional reporting to mentor/client | [5 empty] | 1 hr
D13 (Wk3) | Technical documentation writing standards | [5 empty] | 1 hr
D23 (Wk5) | Presenting technical work: slides + spoken explanation | [5 empty] | 1 hr
D28 (Wk6) | Group discussions, team meeting & collaboration skills | [5 empty] | 1 hr
D38-D39 (Wk8) | Interview verbal skills, body language + mock interview | [5 empty] | 2 hrs
D43 (Wk9) | Reading & presenting EDA reports as portfolio evidence | [5 empty] | 1 hr
D53 (Wk11) | Portfolio talking point: presenting PD results as industry evidence | [5 empty] | 1 hr
D58 (Wk12) | Demo Day presentation structure | [5 empty] | 1 hr
D62 (Wk13) | LinkedIn, email communication | [5 empty] | 1 hr
D65 (Wk13) | Handling tough interview questions | [5 empty] | 1 hr
D69 (Wk14) | Final delivery confidence — panel Q&A handling | [5 empty] | 1 hr
7. Company Visit Policy (tagged OJT, full day)
Total visits | 4 across 14 weeks — one per phase from P2 onward
Frequency | Max 1 visit per 3-week phase
Duration | Full day (8 hrs) — no VILT/SPL/Project-Implementation that day
Trainer accompaniment | Mandatory for every visit
Visit days | D18 (P2 — EDA office/semiconductor fab), D33 (P3 — verification team), D48 (P4 — PD/layout team), D63 (P5 — HR/recruitment team)
8. Vietnam Public Holiday & Working-Day Rules Applied
Weekend exclusion | All Saturdays and Sundays excluded — Mon-Fri only
Vietnam Culture Day | 23-24 Nov 2026 (Mon-Tue) excluded — falls inside the 14-week window
Other 2026 national holidays | New Year (1 Jan), Tet/Lunar New Year (mid-Feb), Hung Kings' Day (Apr), Reunification Day & Labour Day (30 Apr-1 May), National Day (2 Sep) — all fall outside this 21-Sep to 29-Dec-2026 window, so no further skips were needed
Effect on calendar | Skipping 23-24 Nov pushes the 70th working day to 29-Dec-2026 instead of 25-Dec-2026
9. Standard Daily Timing (Technical Day Template)
08:00 - 08:15 | Daily Stand-up (OJT) — progress, plan, blockers
08:15 - 10:15 | VILT — Live Instructor-Led Technical Session
10:15 - 11:30 | Self-Paced Learning (SPL) — guided independent study
11:30 - 12:30 | Lunch break
12:30 - 17:15 | Project Implementation — hands-on build, coding, debugging, docs/GitHub
17:15 - 17:30 | Wrap-up / mentor coaching (OJT)
On Comm-Skills days the OJT block extends (Comm Skills session replaces part of Project Implementation); on Company-Visit days the full 8 hrs is OJT at the host site; on Demo Day (D70) the day is weighted toward OJT for the panel presentation + certificate ceremony. Exact hour split per day is in the 'Session Plan' tab.

## VILT Session Plan
S.No | Week | Day | Date | Topics / Project Details | VILT (Hrs) | SPL (Hrs) | Impl (Hrs) | VILT Proj - Men (hrs) | OJT (hrs) | Remarks
| Week 0 | Day 0 | 2026-09-18 | Program Orientaiom Pre Assessment | 2 | NA | NA | NA | NA | 1. Program Orientation - 1 Hrs 2. Pre Assessment - 1 hr
1 | Week 1 | Day 1 | 2026-09-21 | P1 — Digital Logic Foundation & Scripting | 4 | 75 | 5 |  |  | 1. Trainer will teach the related concepts. 2. Trainer will show the related Demos 3. Git Hub Documentation will be guided by Trainer.
2 |  | Day 2 | 2026-09-22 |  | 4 |  | 5
3 |  | Day 3 | 2026-09-23 | [5 empty] | 8
4 |  | Day 4 | 2026-09-24 |  | 4 |  | 5
5 |  | Day 5 | 2026-09-25 |  | 4 |  | 4
6 | Week 2 | Day 6 | 2026-09-28 |  | NA |  |  | 4
7 |  | Day 7 | 2026-09-29 |  |  |  | 7
8 |  | Day 8 | 2026-09-30 |  |  |  | 7
9 |  | Day 9 | 2026-10-01 | [5 empty] | 8
10 |  | Day 10 | 2026-10-02 |  |  |  | 7
11 | Week 3 | Day 11 | 2026-10-05 | P2 — 8-bit RISC Processor Core (RTL Design) | 4 |  |  |  |  | 1. Trainer will teach the related concepts. 2. Trainer will show the related Demos 3. Git Hub Documentation will be guided by Trainer.
12 |  | Day 12 | 2026-10-06 |  | 4
13 |  | Day 13 | 2026-10-07 | [5 empty] | 8
14 |  | Day 14 | 2026-10-08 |  | 4
15 |  | Day 15 | 2026-10-09 |  | 4
16 | Week 4 | Day 16 | 2026-10-12 |  | NA |  |  | 4
17 |  | Day 17 | 2026-10-13 |  |  |  | 7
18 |  | Day 18 | 2026-10-14 |  |  |  | 7
19 |  | Day 19 | 2026-10-15 | [5 empty] | 8
20 |  | Day 20 | 2026-10-16 |  |  |  | 7
21 | Week 5 | Day 21 | 2026-10-19 |  |  |  | 7
22 |  | Day 22 | 2026-10-20 |  |  |  | 7
23 |  | Day 23 | 2026-10-21 | [5 empty] | 8
24 |  | Day 24 | 2026-10-22 |  |  |  | 7
25 |  | Day 25 | 2026-10-23 |  |  |  | 8
26 | Week 6 | Day 26 | 2026-10-26 | P3 — SystemVerilog + UVM Verification Testbench | 4 |  |  |  |  | 1. Trainer will teach the related concepts. 2. Trainer will show the related Demos 3. Git Hub Documentation will be guided by Trainer.
27 |  | Day 27 | 2026-10-27 |  | 4 |  | 5
28 |  | Day 28 | 2026-10-28 | [5 empty] | 8
29 |  | Day 29 | 2026-10-29 |  | 4 |  | 5
30 |  | Day 30 | 2026-10-30 |  | 4 |  | 5
31 | Week 7 | Day 31 | 2026-11-02 |  | 4 |  |  | 4
32 |  | Day 32 | 2026-11-03 |  | NA |  | 5
33 |  | Day 33 | 2026-11-04 |  |  |  | 5
34 |  | Day 34 | 2026-11-05 | [5 empty] | 8
35 |  | Day 35 | 2026-11-06 |  |  |  | 5
36 | Week 8 | Day 36 | 2026-11-09 |  |  |  | 5
37 |  | Day 37 | 2026-11-10 |  |  |  | 5
38 |  | Day 38 | 2026-11-11 | [5 empty] | 8
39 |  | Day 39 | 2026-11-12 |  |  |  | 5
40 |  | Day 40 | 2026-11-13 |  |  |  | 5
41 | Week 9 | Day 41 | 2026-11-16 | P4 — Full SoC IP Design (RTL to PD Sign-off) | 4 |  |  |  |  | 1. Trainer will teach the related concepts. 2. Trainer will show the related Demos 3. Git Hub Documentation will be guided by Trainer.
42 |  | Day 42 | 2026-11-17 |  | 4 |  | 5
43 |  | Day 43 | 2026-11-18 |  | 4 |  | 5
44 |  | Day 44 | 2026-11-19 | [5 empty] | 8
45 |  | Day 45 | 2026-11-20 |  | 4 |  | 5
46 | Week 10 | Day 46 | 2026-11-23 |  |  |  |  | 4
47 |  | Day 47 | 2026-11-24 |  | 4 |  | 5
48 |  | Day 48 | 2026-11-25 |  | NA |  | 5
49 |  | Day 49 | 2026-11-26 |  |  |  | 5
50 |  | Day 50 | 2026-11-27 | [5 empty] | 8
51 | Week 11 | Day 51 | 2026-11-30 |  |  |  | 5
52 |  | Day 52 | 2026-12-01 |  |  |  | 5
53 |  | Day 53 | 2026-12-02 |  |  |  | 5
54 |  | Day 54 | 2026-12-03 | [5 empty] | 8
55 |  | Day 55 | 2026-12-04 |  |  |  | 5
56 | Week 12 | Day 56 | 2026-12-07 | P5 — Capstone: Full RISC-V Core RTL to GDSII | 4 |  |  |  |  | 1. Trainer will teach the related concepts. 2. Trainer will show the related Demos 3. Git Hub Documentation will be guided by Trainer.
57 |  | Day 57 | 2026-12-08 |  | 4 |  | 5
58 |  | Day 58 | 2026-12-09 |  | 4 |  | 5
59 |  | Day 59 | 2026-12-10 | [5 empty] | 8
60 |  | Day 60 | 2026-12-11 |  | 4 |  | 5
61 | Week 13 | Day 61 | 2026-12-13 |  | 4 |  | 5
62 |  | Day 62 | 2026-12-14 |  | 4 |  | 5
63 |  | Day 63 | 2026-12-15 |  | 4 |  |  | 4
64 |  | Day 64 | 2026-12-16 |  | 3 |  | 5
65 |  | Day 65 | 2026-12-17 |  | NA |  |  |  | 8
66 | Week 14 | Day 66 | 2026-12-20 |  |  |  | 8
67 |  | Day 67 | 2026-12-21 |  |  |  | 8
68 |  | Day 68 | 2026-12-22 |  |  |  | 8
69 |  | Day 69 | 2026-12-23 | [5 empty] | 8
70 |  | Day 70 | 2026-12-24 |  |  |  | 6